## Risk Summary
Table 1
Initiative | Stage | Risk Area | Inherent Risk | Control Coverage | Residual Risk | Owner | Status
Launch U.S.–Philippines Instant Remittance | Risk Assessment | Cross-border payments | High | Medium | Medium | Maya Chen | Resolved
Launch U.S.–Philippines Instant Remittance | Risk Assessment | Sanctions screening | High | Medium | Medium | Daniel Reyes | Resolved
Launch U.S.–Philippines Instant Remittance | Risk Assessment | Fraud and account takeover | Medium | Medium | Medium | Daniel Reyes | Resolved
Launch U.S.–Philippines Instant Remittance | Risk Assessment | Transaction monitoring | High | Low | High | Daniel Reyes | Resolved
Launch U.S.–Philippines Instant Remittance | Risk Assessment | Third-party partner risk | Medium | Low | Medium | Maya Chen | Resolved
Launch U.S.–Philippines Instant Remittance | Risk Assessment | Data privacy and security | Medium | Medium | Medium | Priya Shah | Resolved

## Control Assessment
Table 1
Control ID | Risk Area | Control Description | Control Type | Effectiveness | Control Owner | Evidence | Status
CTRL-001 | Cross-border payments | Initial transaction limit of USD 1,000 per transaction | Preventive | Effective | Maya Chen | Product requirements | Operating
CTRL-002 | Sanctions screening | Screen sender and recipient before funds are released | Preventive | Partially effective | Daniel Reyes | Screening design | Operating
CTRL-003 | Fraud and account takeover | Use step-up authentication and device-risk signals | Preventive | Partially effective | Daniel Reyes | Security design | Operating
CTRL-004 | Transaction monitoring | Monitor velocity, corridor, beneficiary, and unusual activity rules | Detective | Partially effective | Daniel Reyes | Monitoring rules RM-01 to RM-05 | Operating
CTRL-005 | Third-party partner risk | Complete HarborBridge ownership and compliance due diligence | Preventive | Needs improvement | Maya Chen | Partner due-diligence pack | Operating
CTRL-006 | Data privacy and security | Restrict access using role-based permissions and audit logging | Preventive | Effective | Priya Shah | Access-control design | Operating
CTRL-007 | Reconciliation | Reconcile Fulcrum, payment partner, and transaction outcomes | Detective | Needs improvement | Priya Shah | Reconciliation procedure | Operating

## Risk Findings
Table 1
Finding ID | Risk Area | Finding | Impact | Likelihood | Severity | Recommended Action | Assigned To | Due Date
RISK-001 | Cross-border payments | Instant transfers may increase exposure to rapid movement of funds | High | Medium | High | Keep initial limits in place until the 30-day review | Maya Chen | 2026-10-03
RISK-002 | Sanctions screening | Partner screening responsibilities are not fully evidenced | High | Medium | High | Confirm screening ownership and escalation procedures | Daniel Reyes | 2026-09-30
RISK-003 | Fraud and account takeover | New beneficiary and device-risk controls are still being implemented | High | Medium | High | Complete step-up authentication testing | Daniel Reyes | 2026-09-28
RISK-004 | Transaction monitoring | Alert ownership and escalation SLA remain open | High | Medium | High | Document monitoring ownership and response timelines | Daniel Reyes | 2026-09-30
RISK-005 | Third-party partner risk | Beneficial ownership evidence for HarborBridge is incomplete | Medium | Medium | Medium | Complete partner due diligence | Maya Chen | 2026-09-30
RISK-006 | Data privacy and security | Retention and deletion periods require final confirmation | Medium | Low | Medium | Approve data-retention schedule | Priya Shah | 2026-10-05

## Evidence Register
Table 1
Evidence ID | Title | Type | Related Risk | Source | Quality | Status
EV-001 | Instant Remittance Product Brief | Business document | RISK-001 | Synthetic Maya Chen submission | High | Available
EV-002 | HarborBridge Partner Overview | Vendor document | RISK-005 | Synthetic partner pack | Medium | Available
EV-003 | Customer and Recipient Eligibility Design | Product document | RISK-001 | Synthetic product response | Medium | Available
EV-004 | Volume and Transaction Profile | Analysis | RISK-001 | Synthetic product forecast | Medium | Available
EV-005 | Fraud and Authentication Control Proposal | Control document | RISK-003 | Synthetic security design | Medium | Available
EV-006 | Partner Due-Diligence Evidence Pack | Evidence pack | RISK-002, RISK-005 | Synthetic FCRM request | Low | Incomplete
EV-007 | Enhanced Remittance Monitoring Design | Control document | RISK-004 | Synthetic rules RM-01 to RM-05 | Medium | In progress
EV-008 | KYC and Screening Control Attestation | Control attestation | RISK-002 | Synthetic control owner | Medium | Available

## Assessment Summary
Table 1
Field | Value
Initiative | Launch U.S.–Philippines Instant Remittance
Assessment Stage | Risk Assessment
Assessment Type | Synthetic guided-demo assessment
Overall Recommendation | Proceed with conditions
Overall Residual Risk | Medium
Proceed Threshold | 50
Key Open Item | Complete HarborBridge partner due diligence
Key Control Gap | Transaction-monitoring ownership and escalation SLA
Primary Decision Support | Bounded launch with lower initial limits
Next Review | 30-day post-launch FCRM review
Decision Owner | Helen Morgan